## Project Detail
2017
Q1
Project | CSG Resource | Jan |  |  |  |  | Feb |  |  |  | Mar
|  | WK1 (2nd) | WK2 (9th) | WK3 (16th) | WK4 (23rd) | WK5 (30th) | WK6 (6th) | WK7 (13th) | WK8 (20th) | WK9 (27th) | WK10 (6th) | WK11 (13th) | WK12 (20th) | WK13 (27th)
New set tool | Merit Dev1
New set tool | Merit Dev2 | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5
New set tool | Merit Dev3
New set tool | Merit Tester
New set tool | Jamie | [5 empty] | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2
New set tool | Joe | [7 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
New set tool | Zara | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Enhanced consolidation rules | Merit Dev1 | [5 empty] | 1.5 | 3 | 4 | 3 | 3 | 3 | 3 | 3
Enhanced consolidation rules | Merit Dev2
Enhanced consolidation rules | Merit Dev3
Enhanced consolidation rules | Merit Tester | [5 empty] | 1.5 | 2 | 2.5 | 3 | 2 | 2.25 | 2.25 | 3.25
Enhanced consolidation rules | Jamie
Enhanced consolidation rules | Joe | [7 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Enhanced consolidation rules | Zara
New scientist | Merit Dev1
New scientist | Merit Dev2 | [7 empty] | 2 | 2 | 1 | 1 | 1 | 1
New scientist | Merit Dev3
New scientist | Merit Tester | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5
New scientist | Jamie
New scientist | Joe | [7 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
New scientist | Zara | [5 empty] | 3 | 3 | 2 | 1
NPS Dashboard | Merit Dev1
NPS Dashboard | Merit Dev2
NPS Dashboard | Merit Dev3
NPS Dashboard | Merit Tester
NPS Dashboard | Jamie
NPS Dashboard | Joe | [5 empty] | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
NPS Dashboard | Zara
Performance | Merit Dev1
Performance | Merit Dev2 | [9 empty] | 1 | 1 | 1 | 1
Performance | Merit Dev3
Performance | Merit Tester | [9 empty] | 0.5 | 0.5 | 0.5
Performance | Jamie
Performance | Joe | [9 empty] | 0.25 | 0.25 | 0.25 | 0.25
Performance | Zara
Avention/Third party integration | Merit Dev1
Avention/Third party integration | Merit Dev2 | [5 empty] | 1 | 1
Avention/Third party integration | Merit Dev3
Avention/Third party integration | Merit Tester | [5 empty] | 0.5 | 0.5
Avention/Third party integration | Jamie
Avention/Third party integration | Joe | [6 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Avention/Third party integration | Zara
Behavioural data | Merit Dev1 | [5 empty] | 1.5 | 1
Behavioural data | Merit Dev2
Behavioural data | Merit Dev3
Behavioural data | Merit Tester | [7 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Behavioural data | Jamie
Behavioural data | Joe | [5 empty] | 0.25
Behavioural data | Zara
Lights On/Live issues | Merit Dev1 | [5 empty] | 2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Lights On/Live issues | Merit Dev2
Lights On/Live issues | Merit Dev3
Lights On/Live issues | Merit Tester | [6 empty] | 0.5
Lights On/Live issues | Jamie | [5 empty] | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2
Lights On/Live issues | Joe | [5 empty] | 0.25 | 0.25 | 2 | 2 | 2 | 2 | 2 | 2
Lights On/Live issues | Zara
BAU | Merit Dev1 | [7 empty] | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
BAU | Merit Dev2 | [5 empty] | 4 | 4 | 3 | 3 | 2.5 | 2.5 | 2.5 | 2.5
BAU | Merit Dev3
BAU | Merit Tester | [5 empty] | 3 | 2 | 2 | 1.5 | 1.5 | 1.25 | 1.25 | 1.25
BAU | Jamie
BAU | Joe | [5 empty] | 0.25 | 0.25 | 1.5 | 1.5 | 1.25 | 1.25 | 1.25 | 1.25
BAU | Zara | [5 empty] | 1.5 | 1.25 | 1.75 | 2.75
Enhanced Salesforce feed | Merit Dev1
Enhanced Salesforce feed | Merit Dev2
Enhanced Salesforce feed | Merit Dev3
Enhanced Salesforce feed | Merit Tester
Enhanced Salesforce feed | Jamie
Enhanced Salesforce feed | Joe | [9 empty] | 0.25 | 0.25 | 0.25 | 0.25
Enhanced Salesforce feed | Zara | [9 empty] | 4.5 | 4.5 | 4.5 | 4.5
GDPR | Merit Dev1
GDPR | Merit Dev2
GDPR | Merit Dev3
GDPR | Merit Tester
GDPR | Jamie
GDPR | Joe | [7 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
GDPR | Zara
Personal development | Merit Dev1
Personal development | Merit Dev2
Personal development | Merit Dev3
Personal development | Merit Tester
Personal development | Jamie | [10 empty] | 1 | 1 | 1
Personal development | Joe | [5 empty] | 5 | 5 | 0.25 | 0.25
Personal development | Zara
Individual
Merit Dev1 | Dev | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Merit Dev2 | Dev | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Merit Dev3 | Dev | 5 | 5 | 5
Merit Tester | Test | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Jamie | Support | 5 | 5 | 4 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Joe | Tech lead | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Zara | BA |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total Alllocation | Merit Dev1 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Merit Dev2 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Merit Dev3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Merit Tester | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Jamie | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Joe | 0 | 0 | 0 | 0 | 0 | 6 | 5.75 | 5 | 5 | 5 | 5 | 5 | 5
| Zara | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5

## Types of resource
Percentage of Joe time
Resource | Tasks | Who
Developer | Undertake development and specified in user story | Merit |  | Tech Lead
| Undertake ad hoc back-end trouble-shooting of bugs and failures |  |  | App Sup
Application Support | Creating/managing users | Jamie |  | App Config
| Manage application configuration |  |  | Tech Lead
| Trouble-shooting application errors |  |  | Dev 1
| Support use of application |  |  | Dev 2
| Monitor product performance |  |  | Tester
Trainer | Train users on product | Jamie
Business Analyst | Understand and document requirement | Zara
Architect | Writing technical user stories | Joe | 15
Devising data and solution models
Supporting BA with technical/process knowledge
Tester | Test development task | Merit
Manage regression testing
Product manager | Manage backlog | Joe | 20
Understand Product Owner's priorities and manage system roadmap
Work with Development Manager to assign tasks to sprint
Project management (?)
Development Manager | Resource management | Joe | 20
Manage development process
Manage development team
Manage release process
Development DBA | Manage pre-production databases | Joe | 10
Support database development eg ensuring database remain performant
2nd line support |  | Joe | 30
30